## Sheet1
Backup Plan for Solutions Portfolio MDM Activities
# | Activitivy | Owner | Remark | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01
1 | Item queries, creation and maintenance - PDH and ISF | Carole Hamilton |  |  | In progress
1.1 | PDH and ISF access - Carole and Nabhaan | Item-MDM team |  | Complete
1.2 | PDH and ISF training: https://canoneuropenv.sharepoint.com/teams/EMEA-MDM/1Documents/Forms/AllItems.aspx?csf=1&web=1&e=4f9H4m&FolderCTID=0x012000406F93156F4B2A428E8E3943AFA7C284&id=%2Fteams%2FEMEA%2DMDM%2F1Documents%2F2%2EManuals%2F2%2EProduct%2F1%2EAccenture%5FManuals | Luiz Fernando Tossi Silva | Transfer knowledge to Carole to access and use PDH and Sumatra for item queries as well as using ISF for item maintenance. |  | In progress
1.3 | PLC Maintenace training: https://canoneuropenv.sharepoint.com/teams/EMEA-MDM/1Documents/Forms/AllItems.aspx?id=%2Fteams%2FEMEA%2DMDM%2F1Documents%2F1%2EQuality%5FDocuments%2F2%2EProduct%2FProduct%20Life%20Cycle%20Management%20Overview%20document%5FV%2E1%2E5%20%282%29%2Epdf&parent=%2Fteams%2FEMEA%2DMDM%2F1Documents%2F1%2EQuality%5FDocuments%2F2%2EProduct | Luiz Fernando Tossi Silva | Transfer knowledge to Carole to maintain PLC through ISF. |  | In progress
2 | Stock provision revision | Carole Hamilton | Data asset control on a quarterly basis as per reports sent by EDSM and Finance teams.
2.1 | 2025 - Q1 Review: https://canoneuropenv.sharepoint.com/:x:/r/teams/PBD/ProjectRooms/_layouts/15/Doc.aspx?sourcedoc=%7Bf6ff0cc6-fa2d-4e50-8706-48d20e70fff3%7D&action=edit&wdenableroaming=1&wdlcid=en-US&wdorigin=ItemsView&wdhostclicktime=1741000901030&wdredirectionreason=Force_SingleStepBoot&wdinitialsession=9fbab2b0-5ef4-d578-19b3-6ede9609b3d4&wdrldsc=2&wdrldc=1&wdrldr=ContinueInExcel | Luiz Fernando Tossi Silva |  | Complete
2.2 | 2025 - Q2 Review | Carole Hamilton
3 | Model and items release in Pearl Chain / CPQ | Nabhaan Shahid
3.1 | Release plan alignment: https://canoneuropenv.sharepoint.com/:x:/r/teams/PBD/ProjectRooms/_layouts/15/Doc.aspx?sourcedoc=%7B408acc89-41de-4fd4-a486-91b7788c7572%7D&action=edit&wdenableroaming=1&wdlcid=en-US&wdorigin=Other&wdredirectionreason=Force_SingleStepBoot&wdinitialsession=77d71ad1-eb88-8653-4d3a-a8c5e121b115&wdrldsc=3&wdrldc=1&wdrldr=ContinueInExcel | Nabhaan Shahid
4 | Pricing maintenance and support to NSO in PearlChain. Support material: https://canoneuropenv.sharepoint.com/:p:/r/teams/PBD/ProjectRooms/_layouts/15/Doc.aspx?sourcedoc=%7BF5E87BDB-5DA8-46E3-BBD2-19F2811855C4%7D&file=Product%20_%20Pricing%20Training.pptx&action=edit&mobileredirect=true | Nabhaan Shahid
5 | Working - Release catch up, MDM NSO assistance, etc. | Luiz Fernando Tossi Silva
5.1 | Working in April: 16th, 23rd | Luiz Fernando Tossi Silva |  | N/A | N/A
5.2 | Working in May: 1st, 2nd, 8th, 9th, 15th, 16th, 22nd, 23rd | Luiz Fernando Tossi Silva |  | N/A | N/A
5.3 | UFO Project release | Luiz Fernando Tossi Silva |  | Complete | In progress